## TimeLine
Id | TimeLineId | Year | Month | Day | Name | AnnTitle | AnnLabel | Description | AnnDX | AnnDY | AnnType | AnnConnectorEnd | AnnLineType
1 | 1 | 2023 | 5 | 1 | MDM | MDM | Business Project Start | Implement MDM solution using Syniti. This project consists of following sub projects relevant to GDP: 1. Migration of master data to Syniti; 2. Golden Record; 3. Data Quality. | 1 | -20 | elbow | dot | vertical
1 | 1 | 2024 | 1 | 1 | MDM | MDM - GDP | GDP Project Start |  | -50 | -20 | threshold | dot | vertical
2 | 1 | 2024 | 3 | 11 | MDM | MDM - GDP | GDP Deadline - Migration |  | -1 | -60 | elbow | dot | horizontal
3 | 1 | 2024 | 9 | 1 | MDM | MDM - GDP | GDP Deadline Golden Record |  | 10 | -20 | threshold | dot | vertical
4 | 1 | 2024 | 12 | 31 | MDM | MDM - DQ | GDP Deadline Data Quality |  | 10 | -20 | elbow | arrow | vertical
5 | 2 | 2024 | 1 | 1 | OneHR | OneHR | Business Project Start | Implement a global HR system using Success Factors. | -10 | -20 | elbow | dot | vertical
6 | 2 | 2024 | 4 | 1 | OneHR | OneHR | GDP Project Start |  | -5 | -40 | elbow | dot | horizontal
6 | 2 | 2024 | 6 | 31 | OneHR | OneHR | Development End |  | -1 | -20 | elbow | dot | horizontal
| 2 | 2024 | 7 | 12 | OneHR | OneHR | SIT End |  | 1 | -45 | elbow | dot | vertical
| 2 | 2024 | 8 | 31 | OneHR | OneHR | UAT End |  | 1 | -20 | elbow | dot | vertical
6 | 2 | 2024 | 10 | 1 | OneHR | OneHR | Project End |  | 80 | -20 | elbow | dot | vertical
5 | 3 | 2024 | 1 | 1 | OneStream | OneStream Start | Business Project Start | Implement a global Financial Consolidation system using OneStream. | -10 | -20 | elbow | dot | vertical
5 | 3 | 2025 | 6 | 31 | OneStream | OneStream End | Business Project End |  | 90 | -10 | elbow | dot | vertical
5 | 3 | 2024 | 4 | 1 | OneStream | GDP | GDP Project Start |  | -5 | -40 | elbow | dot | horizontal
6 | 3 | 2024 | 10 | 31 | OneStream | Financial Statements | Business Deadline (Manual) |  | -40 | -20 | elbow | dot | horizontal
5 | 3 | 2025 | 2 | 1 | OneStream | Additional Reporting | GDP Deadline - Additional Reporting |  | -10 | -20 | elbow | dot | vertical
5 | 3 | 2025 | 3 | 1 | OneStream | Exchange Rates | GDP Deadline - Exchange Rates |  | 1 | -20 | elbow | dot | vertical
5 | 3 | 2025 | 6 | 1 | OneStream | GDP Dataflow | GDP Deadline - Dataflow OneStream -> GDP |  | 20 | -20 | elbow | dot | vertical
5 | 4 | 2024 | 1 | 1 | LatamGDP | Latam SAP to GDP | GDP Project Start | Onboard the SAP system used in Latam South to GDP | -10 | -20 | elbow | arrow | vertical
5 | 4 | 2024 | 12 | 1 | LatamGDP | Latam SAP to GDP | GDP Project End |  | 10 | -20 | elbow | dot | vertical
5 | 5 | 2024 | 1 | 1 | ApacGDP | Apac JDE to GDP | GDP Project Start | Onboard the JDE system used in Apac to GDP | -10 | -20 | elbow | dot | vertical
5 | 5 | 2024 | 12 | 1 | ApacGDP | Apac JDE to GDP | GDP Project End |  | 60 | -20 | elbow | dot | vertical
| 6 | 2024 | 5 | 1 | Sales Order Snapshot | Sales Order Snapshot for North America | GDP Project Start |  | -20 | -10 | elbow | dot | vertical
| 6 | 2024 | 6 | 31 | Sales Order Snapshot | Sales Order Snapshot for North America | Business Deadline |  | 10 | -10 | elbow | dot | vertical
| 7 | 2024 | 5 | 1 | Predictive Pricing Tool | Predictive Pricing Tool |  |  | -20 | -20 | elbow | dot | vertical
| 7 | 2024 | 9 | 1 | Predictive Pricing Tool | Predictive Pricing Tool | Business Deadline |  | 10 | -20 | elbow | dot | vertical
| 8 | 2025 | 1 | 1 | Migrate DWHs to GDP | Migrate DWHs to GDP |  |  | 10 | -20 | elbow | dot | vertical
| 8 | 2026 | 12 | 31 | Migrate DWHs to GDP | Migrate DWHs to GDP |  |  | 10 | -20 | elbow | dot | vertical
| 9 | 2024 | 6 | 12 | Digital/PIM | Digital: Customer/Product/OrderHistory | GDP Project Start |  | 10 | -20 | elbow | dot | vertical
| 9 | 2024 | 9 | 31 | Digital/PIM | Digital: Customer/Product/OrderHistory | Business Deadline |  | 10 | -20 | elbow | dot | vertical
| 10 | 2024 | 8 | 7 | RFP | 1. Caldic shares RFP with shortlisted vendors |  |  | 0 | -20 | elbow | dot | vertical
| 10 | 2024 | 8 | 16 | RFP | 1.1 Shortlisted vendors submit questions for Q&A |  |  | 0 | 10 | elbow | dot | vertical
| 10 | 2024 | 8 | 26 | RFP | 1.2 Caldic provides question responses |  |  | 0 | 40 | elbow | dot | vertical
| 10 | 2024 | 9 | 4 | RFP | 1.3 Vendors submit proposal |  |  | 0 | 70 | elbow | dot | vertical
| 10 | 2024 | 9 | 16 | RFP | 1.4 Vendors pitch proposal (Demo) |  |  | 0 | 100 | elbow | dot | vertical
| 10 | 2024 | 9 | 30 | RFP | 2 Caldic communicates selection for final round |  |  | 0 | 130 | elbow | dot | vertical
| 10 | 2024 | 10 | 4 | RFP | 2.1 Selected vendor submit final proposal |  |  | 0 | 160 | elbow | dot | vertical
| 10 | 2024 | 10 | 31 | RFP | 2.2 Final pitch, discussion and questions |  |  | 0 | 190 | elbow | dot | vertical
| 10 | 2024 | 10 | 31 | RFP | 3 Target date to start project ramp-up and get foundations in place |  |  | 0 | 220 | elbow | dot | vertical

## LOV
Level | Type
0 | Root
1 | Capability Area
2 | Data Capability
3 | Service
4 | Service Capability
5 | Service Maturity
MaxChildId | #REF!