## TimeLine
Id | TimeLineId | Year | Month | Day | Name | AnnTitle | AnnLabel | Description | AnnDX | AnnDY | AnnType | AnnConnectorEnd | AnnLineType
| 10 | 2024 | 8 | 7 | RFP | RFP | 1. Caldic shares RFP with shortlisted vendors |  | 0 | -20 | elbow | dot | vertical
| 10 | 2024 | 8 | 16 | RFP | RFP | 1.1 Shortlisted vendors submit questions for Q&A |  | 0 | -20 | elbow | dot | vertical
| 10 | 2024 | 8 | 26 | RFP | RFP | 1.2 Caldic provides question responses |  | 0 | -20 | elbow | dot | vertical
| 10 | 2024 | 9 | 4 | RFP | RFP | 1.3 Vendors submit proposal |  | 0 | -20 | elbow | dot | vertical
| 10 | 2024 | 9 | 16 | RFP | RFP | 1.4 Vendors pitch proposal (Demo) |  | 0 | -20 | elbow | dot | vertical
| 10 | 2024 | 11 | 7 | RFP | RFP | 2 Caldic communicates selection for final round |  | -10 | -20 | elbow | dot | vertical
| 10 | 2024 | 11 | 10 | RFP | RFP | 2.1 Selected vendor submit final proposal |  | 5 | -20 | elbow | dot | vertical
| 10 | 2024 | 11 | 14 | RFP | RFP | 2.2 Final pitch, discussion and questions |  | 90 | -20 | elbow | dot | vertical
| 10 | 2024 | 12 | 31 | RFP | RFP | Choice of new partner |  | -20 | -20 | elbow | dot | vertical
| 10 | 2025 | 1 | 1 | RFP | RFP | Start collaboration with new vendor |  | 0 | -20 | elbow | dot | vertical

## LOV
Level | Type
0 | Root
1 | Capability Area
2 | Data Capability
3 | Service
4 | Service Capability
5 | Service Maturity
MaxChildId | #REF!

## Original
Original Planning
2024 | 8 | 7 | RFP | RFP | 1. Caldic shares RFP with shortlisted vendors
2024 | 8 | 16 | RFP | RFP | 1.1 Shortlisted vendors submit questions for Q&A
2024 | 8 | 26 | RFP | RFP | 1.2 Caldic provides question responses
2024 | 9 | 4 | RFP | RFP | 1.3 Vendors submit proposal
2024 | 9 | 16 | RFP | RFP | 1.4 Vendors pitch proposal (Demo)
2024 | 9 | 30 | RFP | RFP | 2 Caldic communicates selection for final round
2024 | 10 | 4 | RFP | RFP | 2.1 Selected vendor submit final proposal
2024 | 10 | 31 | RFP | RFP | 2.2 Final pitch, discussion and questions
2024 | 10 | 31 | RFP | RFP | 3 Target date to start project ramp-up and get foundations in place